## Sheet1
ID | User Story | Acceptance Criteria | Feature | Sprint | Story Points
US_01 | As a user, I want a dashboard to view phishing email history so that I can track past threats. | Dashboard displays list of phishing emails with filtering options. | Dashboard & Reporting | Sprint 1 | 5
US_02 | As a user, I want to filter emails based on risk level so that I can quickly identify dangerous emails. | System allows filtering by safe, suspicious, and phishing categories. | Phishing Email Filtering | Sprint 1 | 3
US_03 | As an admin, I want to view statistics on detected threats so that I can analyze system performance. | Dashboard provides statistics on phishing, fraud, and malicious URLs. | Threat Statistics | Sprint 1 | 8
US_04 | As an admin, I want to manage user roles and permissions so that I can control access levels. | System supports different access levels for users and admins. | User Management | Sprint 1 | 8
US_05 | As a user, I want to upload an email for phishing detection so that I can know if it's safe. | System classifies email as safe, suspicious, or phishing with an alert. | Phishing Email Detection | Sprint 2 | 8
US_06 | As a user, I want to upload transaction data so that I can detect fraudulent activities. | System flags transaction as normal or suspicious with a confidence score. | Fraudulent Transaction Detection | Sprint 2 | 13
US_07 | As a user, I want to check if a URL is malicious so that I can avoid phishing sites. | System checks URL structure and domain reputation, classifying it as safe, suspicious, or malicious. | URL Classification | Sprint 2 | 5
US_08 | As a user, I want to verify if a sender email is trustworthy so that I can decide whether to engage with the sender. | System checks sender reputation and displays a trust score. | Sender Reputation Check | Sprint 2 | 8
US_09 | As a user, I want to receive real-time alerts for detected threats so that I can take immediate action. | User receives notifications via email or app for detected threats. | Real-time Alerts | Sprint 3 | 8
US_10 | As a user, I want an option to report a false positive classification so that I can help improve detection accuracy. | Users can flag an incorrect detection for review. | User Feedback System | Sprint 3 | 3
TS_01 | Create a dashboard for threat statistics so that admins can monitor system performance. | Dashboard displays data on detected threats. | Threat Statistics | Sprint 1 | 8
TS_02 | Design a user role management system so that access levels can be controlled efficiently. | Admins can assign permissions to different user roles. | User Management | Sprint 1 | 8
TS_03 | Implement OAuth authentication for secure user access so that users can log in securely. | User authentication is secure, and access tokens work correctly. | Security & Authentication | Sprint 1 | 5
TS_04 | Set up AWS for cloud deployment so that the system can be scalable and accessible. | Backend deployed and accessible via API. | Cloud Deployment | Sprint 1 | 5
TS_05 | Integrate BERT model for phishing email detection so that emails can be classified accurately. | Model achieves at least 90% accuracy on test data. | AI Model Training | Sprint 2 | 8
TS_06 | Implement Autoencoder + Isolation Forest for fraud detection so that anomalies in transactions can be detected. | Model correctly classifies anomalies in dataset. | AI Model Training | Sprint 2 | 13
TS_07 | Deploy CNN + LSTM model for URL detection so that phishing websites can be identified. | Model classifies URLs with at least 85% accuracy. | AI Model Training | Sprint 2 | 8
TS_08 | Implement email sender verification model so that sender reputation can be assessed. | System provides a sender trust score based on reputation. | Sender Reputation Check | Sprint 2 | 5
TS_09 | Develop a notification system for real-time alerts so that users are informed of potential threats. | Users receive accurate notifications for detected threats. | Notification System | Sprint 3 | 8
TS_10 | Develop a feedback mechanism for false positive reports so that the system can improve over time. | Users can flag and submit incorrect classifications for review. | User Feedback System | Sprint 3 | 3